## Local Rec calendar summary
|  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2
| 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01
SF FSTF Calendar 2023-2024
CCSF Budget Cycle | 2022-12-01: Departments Develop Proposed Budget; 2023-03-01: Mayor & Office of Public Policy & Finance Review; 2023-06-01: Board of Supervisors Review & Enactment of Budget; 2023-12-01: Departments Develop Proposed Budget; 2024-03-01: Mayor & Office of Public Policy & Finance Review; 2024-06-01: Board of Supervisors Review & Enactment of Budget
Budget Deadlines | 2022-10-01: Budget Instructions Issued; 2023-01-01: Department Submit Budget Requests; 2023-04-01: Mayor Submits Enterprise Dept Budget; 2023-05-01: Mayor Submits General Fund Dept & Capital Budgets; 2023-06-01: BOS Review + Add Backs; 2023-07-01: Budget Enacted; 2023-08-01: Mayor Signs Budget; 2023-12-01: Budget Instructions Issued; 2024-02-01: Department Submit Budget Requests; 2024-04-01: Mayor Submits Enterprise Department Budget; 2024-05-01: Mayor Submits General Fund Department & Capital Budgets; 2024-07-01: Budget Enacted; 2024-08-01: Mayor Signs Budget; 2024-12-01: Budget Instructions Issued | Budget Instructions Issued |  |  | Department Submit Budget Requests |  |  | Mayor Submits Enterprise Dept Budget | Mayor Submits General Fund Dept & Capital Budgets | BOS Review + Add Backs
| 2022-10-01: Q2; 2023-01-01: Q3; 2023-04-01: Q4; 2023-07-01: Q1; 2023-10-01: Q2; 2024-01-01: Q3; 2024-04-01: Q4; 2024-07-01: Q1; 2024-10-01: Q2 | Q2 |  |  | Q3 |  |  | Q4
| 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2023-10-25 | 2023-11-25 | 2023-12-25 | 2024-01-25 | 2024-02-25 | 2024-03-25 | 2024-04-01 | 2024-05-01 | 2024-06-01
FSTF Meetings
Agenda items related to 2022 Recommendations
FSTF Staffing: Full-time (FT) and .5 position | 2022-09-01: Post FSTF FTE position "Health Coordinator 2"; onboard .5 FTE staff; 2022-10-01: Continue onboarding .5 FTE staff; 2023-01-01: Interview & select FY candidate; onboard new FT staff; 2023-04-01: Complete
2024 Recommendations | 2022-10-01: 1) Update 2022 recommendations (approve Nov/Dec Meeting); Graphic design; 2023-01-01: Finalize recs; set up meetings; prep slide deck; disseminate recommendations; complete 80% of meetings; develop next steps from meetings; 2023-04-01: Follow-up meetings; implement identified next steps; 2023-10-01: Food Equity Report deadline | Begin pulling data for 2024 Recommendations, developing narrative and framework |  |  | 2024 Recommendations finalized in March Nourish California/FRAC to present on state and federal legislative agenda |  |  | Proposed hearing to present on 2024 Recommendations Nourish California/FRAC to present on state and federal legislative agenda
Funding Equity - Special Revenue | 2022-09-01: Identify which groups oversee special revenue ( i.e. Prop C); 2023-01-01: Schedule meetings with groups oversee special revenue (i.e. Prop C) re: plans to address food/nutrition security
Budget Asks | 2022-09-01: Initial discussion about SF budget cycle; 2023-01-01: Determine FSTF budget ask guidelines/role; develop next steps | Utilize BFSER for development of budget asks |  |  | See "Recommendations"
FSTF Configuration | 2022-10-01: New member recruitment; 2023-01-01: New member confirmation and on-boarding; 2023-07-01: New member nominations | FSTF elects new chair and vice-chair (October)
Ensuring Community Voice & Community Leadership | [31 empty] | Begin developing BFSER briefs |  |  | Share BFSER briefs with community-based organizations through community meetings | bar: 2022-09-01 to 2022-12-01; 2023-10-01 to 2024-12-01
Issue Action Areas
Housing & Food | 2022-09-01: Recruit via email for sub-committees: reach out to Anne Quaintance see if she will lead this; 2023-01-01: 1) Conveen group to develop issue/info brief:; 2023-07-01: Check in with Anne re: what support is needed from FSTF
Medi-cal/CalAIM | 2022-09-01: Schedule meeting with SF Health Plans about adopting food interventions w/CA advancing & innovative Medi-Cal; 2022-10-01: Schedule & Meet with SF Health Plan;; 2023-01-01: Update in FSTF Mtgs; determine next steps; 2023-04-01: SF Health Plan to opt into full spectrum of MSF interventions by June 2023 | [6 empty] | Presentation by Health Plans around plans for Medically Supportive Food and Nutrition
Centralized Food Body within Gov | 2023-07-01: 1) form steering group 2) create 2 pager summary 3) launch first subcommittee meeting | Continue hosting subcommittee meetings, establish roles, actionable goals of subcommittee |  |  | Continue hosting subcommittee meetings, interviewing food policy bodies, refine and prioritize criteria |  |  | Develop recommendations to bring to full task force to vote on, present final recommendations to city leaders
Food Equity Report | 2022-09-01: Schedule meeting with DPH (Ayanna Bennett?) on plan for Food Equity Report & how FSTF can support. Ask DPH for a timeline.; 2022-10-01: Schedule meeting with DPH (Ayanna Bennett) on plan for Food Equity Report & how FSTF can support. Ask DPH for a timeline.; 2023-01-01: 1) FSTF develops expectations for report and how FSTF is involved; 2) meet with DPH about Food Equity Report and info required; 3) develop timeline & next steps; 2023-04-01: Data gathering; 2023-07-01: Develop recommendations; Hold special meetings: 8/30 and 9/19 Input and review; Oct Deadline | Hold special meetings in October and November, new report deadline of December 1 |  |  | Begin planning phase of BFSER 2.0. FSTF to provide input on changes |  |  | DPH Report Team to provide updates to FSTF on timeline/process for 2025 Biennial Food Security and Equity Report
Funding for Equity | 2023-01-01: Included in Recommendations 2023 - including equitable food supports | Utilize BFSER for development of equity-focused asks
Funding for Equity: Special | 2022-09-01: Recruit via email for sub-committees; 2022-10-01: Hold 1st meeting
Funding for Equity: General
Funding for Equity: Other
Food Recovery | 2022-10-01: Determine timeline; Schedule & Meet with SF Environment about SB 1383; 2023-04-01: Complete; 2023-07-01: SFE - Food Recovery Convening kick off
Community Food Policy Body | 2022-09-01: Meet with steering committee members to see how FSTF can support efforts/collaborate et al.; 2023-01-01: Meet with FAACTS and other groups to see how FSTF can support efforts/collaborate, etc.; 2023-04-01: Continue to meet with groups; 2023-07-01: Continue to meet with groups | See line 20
Meet with Gov. Officials/Dept. Leads
HSH Director, Shireen Mcspadden | 2022-09-01: AQ initial conversation, will let FSTF know next steps; 2023-01-01: Schedule and conduct meetings | Schedule and meet with Directors after FSTF recommendations are ready | [5 empty] | Schedule and meet with Directors and BOS after FSTF recommendations and BFSER are ready DPH Report Team is presenting the BFSER at the Health Commission on April 2nd
HSA Director, Trent Rhorer
DPH Director, Grant Colfax
DAS Director, Kelly Dearman
BOS District 1: Connie Chan | 2023-01-01: Schedule and conduct meetings; determine next steps
BOS District 2: Catherine Stefani
BOS District 3: Aaron Peskin
BOS District 4: Joel Engardio
BOS District 5: Dean Preston
BOS District 6: Matt Dorsey
BOS District 7: Myrna Melgar
BOS District 8: Rafael Mandelman
BOS District 9: Hillary Ronen
BOS District 10: Shamann Walton
BOS District 11: Ahsha Safai
Emerging Issues
Rising Food Costs | bar: 2022-09-01 to 2022-12-01; 2023-10-01 to 2024-12-01
Disaster Food Planning | 2022-10-01: Reach out to DEM | Asked DEM or other city dept to present at FSTF on 9/22
HOTC Farmers Market - Food Access | 2023-07-01: Monitoring - FSTF sent letter urging no negative impacts to vendors/residents with relocation
More Info
Whole Household Coverage | [28 empty] | Reviewing responses from reporting agencies for BFSER | bar: 2022-10-01 to 2022-12-01
Info & Referal - Outreach | [28 empty] | To be included in BFSER | bar: 2022-10-01 to 2022-12-01
Info & Referal - Centralized | [28 empty] | To be included in BFSER | bar: 2022-10-01 to 2022-12-01
Direct Cash Benefits | bar: 2022-10-01 to 2022-12-01
Urban Agriculture | [28 empty] | To be included in BFSER, Parks and Rec. reporting agency provided data | bar: 2022-10-01 to 2022-12-01
Transportation | [28 empty] | Brief to be included in BFSER | bar: 2022-10-01 to 2022-12-01